## Example
Project Diary: <Project Name>
Week: 16
Assignee | Duration (hours) | Task | Artifact | Notes
Jörges | 0.5 | Created project diary | project-diary.xslx | Statistics to be added!
Schmidt | 0.5 | Created first version of requirements document | requirements.md | Created document with basic structure
Schmidt, Jörges | 4.25 | Modeled use cases | requirements/uml/* | Setting up the UML tool took a while…
Meier | 1.5 | Created mockup of the main page | mainpage.png | Futher pages coming soon

## Week 1
Project Diary: Binary Codesmiths
Week: 1 | 2001-04-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 1 | LAB 1 | Setup Teams, lab docs, GitHub repo https://github.com/IanMurnane/dmsa-sose25-Binary | Team name: Binary
Sraboni | 1 | Strategy behaviour pattern | DMSA (1st presentation).pptx | made the presentation slide
Ian | 0.1 | Present Strategy behaviour pattern | DMSA (1st presentation).pptx

## Week 2
Project Diary: Binary Codesmiths
Week: 2 | 2008-04-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 2 | LAB 2 |  | LAB 2 - Create Wiki, DB diagrams, update requirements
Sraboni | 2 | LAB 2 |  | Updating Wiki, Class Diagram

## Week 3
Project Diary: Binary Codesmiths
Week: 3 | 2015-04-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 2 | LAB 3 | https://github.com/IanMurnane/dmsa-sose25-Binary-Codesmiths/blob/main/Documentation/Images/context_mapping.png | Identify bounded contexts, update wiki
Sraboni | 0.5 | LAB 3 |  | Bounded Context identification
Sraboni | 1 | LAB 3 | https://github.com/IanMurnane/dmsa-sose25-Binary-Codesmiths/blob/main/Documentation/Images/context_mapping.png | context mapping design, updated wiki

## Week 4
Project Diary: Binary Codesmiths
Week: 4 | 2022-04-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 2 | LAB 4 |  | Updated wiki, added various uml diagrams
Sraboni | 2 | LAB 4 | https://github.com/IanMurnane/dmsa-sose25-Binary-Codesmiths/blob/main/Documentation/Images/paymentContext.png | tactical designing for Payment context
Sraboni | 0.5 | LAB 4 |  | Event Storming

## Week 5
Project Diary: Binary Codesmiths
Week: 5 | 2029-04-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 2 | LAB 5 |  | setup spring boot template app
Sraboni | 1 | LAB 5 |  | implementation started, setting up SprinBoot app

## Week 6
Project Diary: Binary Codesmiths
Week: 6 | 2006-05-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 2 | LAB 5 |  | setup db, continue implementing vehicle-microservice
Sraboni | 2 | LAB 5 |  | implemented payment-microservice, debugging

## Week 7
Project Diary: Binary Codesmiths
Week: 7 | 2013-05-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 2 | LAB 5 |  | continue biulding microservice, postman testing
Sraboni | 2 | LAB 5 |  | setting up DB, testing API using POSTMAN

## Week 8
Project Diary: Binary Codesmiths
Week: 7 | 2020-05-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 8 | LAB 5 | vehicle-management-service bounded context | Completed basic working vehicle-management-service, saved postman collection

## Week 9
Project Diary: Binary Codesmiths
Week: 7 | 2027-05-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 2 | LAB 5 |  | Built Eureka test and checked calling microservices through other microservices by name using postman was successful.

## Week 10
Project Diary: Binary Codesmiths
Week: 7 | 2003-06-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 3 | LAB 5 |  | Updated all configs to yml, pointing to the config server

## Week 11
Project Diary: Binary Codesmiths
Week: 7 | 2010-06-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 4 | LAB 5 |  | Added CORS to all services. Updated readme.md.

## Week 12
Project Diary: Binary Codesmiths
Week: 7 | 2017-06-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 10 | LAB 6 |  | Built frontend to display map, plot vehicles, info box, vehicle info, booking, logins, payment, ratings. File cleanup. Added OpenFeign and pointed all api calls to booking-service.

## Week 13
Project Diary: Binary Codesmiths
Week: 7 | 2024-06-01
Assignee | Duration (hours) | Task | Artifact | Notes
Ian | 4 | LAB 7 |  | Fixed frontend-provider api to demo getVehicle calls. Added lemma for vehicle-service. Added preloaded data.sql for vehicles. Created class diagram.

## Week 14
Project Diary: Binary Codesmiths
Week: 7 | 2001-07-01
Assignee | Duration (hours) | Task | Artifact | Notes

## Week 15
Project Diary: Binary Codesmiths
Week: 7 | 2008-07-01
Assignee | Duration (hours) | Task | Artifact | Notes